## Technical Analysis
Whizard Issue Tracker
S.No. | Module | Item Description | New Requirement / Change Request / Issue | Type | Next Action | Responsibility | Resolution Date | Status | Likely Code Area | Probable Root Cause | Suggested Fix / Investigation Hint | Current Status
6 | Navigation | Remove Manage Skill Option | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/layout/ + route/menu configuration | Sidebar/menu configuration is likely stale, conditionally hidden, or missing the expected icon binding. | Inspect navigation config, role-based visibility flags, and icon mapping for the affected menu entries.
7 | Navigation | Icon not showing for manage company | Issue | Functional | showing in my case | Puneet | 2026-06-04 | Done | apps/web/admin-portal/src/app/layout/ + route/menu configuration | Sidebar/menu configuration is likely stale, conditionally hidden, or missing the expected icon binding. | Inspect navigation config, role-based visibility flags, and icon mapping for the affected menu entries.
20 | Manage Industry WRCF | Should show proficiency level like capability … Label (Level) | Issue | UI | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/ | The display-label builder is inconsistent across modules and is concatenating or omitting label metadata incorrectly. | Centralize label formatting for capability/proficiency and reuse a single formatter across dropdowns and panels.
21 | Manage Industry WRCF | Change icon for Upload and download template | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/ | Template action buttons are using placeholder or outdated icon assets. | Swap the icon bindings/assets to the approved upload/download set and verify hover/disabled states.
22 | Manage Industry WRCF | Should show default industry sector and industry selected 1. From Navigation, should show default first value selected 2. From Edit Structure, should show default dashboard selected values | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ + apps/web/admin-portal/src/app/pages/industry-wrcf/ | Dashboard quick-action navigation likely does not preserve selected sector/industry in route state, query params, or shared store. | Pass selected dashboard context into Edit Structure navigation and hydrate the Manage Industry WRCF page from that context before defaulting.
23 | Manage Industry WRCF | Should show Industry sector and industry in alphabetic sorted order (ascending) | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/ | The list is likely rendered in API/default insertion order because no explicit sort is applied before binding the dropdown/list. | Apply deterministic ascending sort in the data adapter or UI mapping before rendering the list. | 2026-04-09 - Still exists
24 | Manage Industry WRCF | Should show default first value selected for FG, PWO and SWO, capability and Proficiency (in green if any mapped) | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/ | Child list selection is likely not triggered after data load or after parent filter/context changes. | After loading each child collection, explicitly select the first available item and refresh downstream panels. | 2026-04-09 - Still exists
25 | Manage Industry WRCF | Should show FG, PWO and SWO in alphabetic order | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/ | The list is likely rendered in API/default insertion order because no explicit sort is applied before binding the dropdown/list. | Apply deterministic ascending sort in the data adapter or UI mapping before rendering the list. | 2026-04-09 - Still exists
26 | Functional Group | Should allow only 50 character with name | Issue | UI | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Name input is likely missing a max-length validator or the limit is not enforced consistently between UI and backend. | Add matching max-length validation in both form validators and backend DTO/entity rules.
27 | Functional Group | Should show Domain type in ascending alphabetic order | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | The list is likely rendered in API/default insertion order because no explicit sort is applied before binding the dropdown/list. | Apply deterministic ascending sort in the data adapter or UI mapping before rendering the list.
28 | Functional Group | Should not allowed duplicate name for same industry in Add and Edit | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Uniqueness validation is likely missing, scoped incorrectly, or only checked on create but not edit. | Enforce scoped duplicate-name validation in backend and surface the same error path in both add and edit flows.
9 | Create New User | In Password, Show/Hide to be align with box | Issue | UI |  | Yagyesh | 2026-06-04 | Done | User creation form component/template and CSS | Password toggle icon is likely positioned with absolute styling that does not match the current input height/padding. | Adjust the input wrapper CSS and icon anchor so the visibility toggle aligns with the form control.
10 | Create New User | E-mail and Email Address, what is the difference | Issue | UI |  | Yagyesh | 2026-06-04 | Done | User creation form labels / translation constants | Different labels are probably coming from mixed hardcoded text or inconsistent translation keys. | Standardize one label string and reuse it across create/edit/list/detail surfaces.
11 | Create New User | Should option for confirm password | Issue | UI |  | Yagyesh | 2026-06-04 | Done | User creation/onboarding form component, validators, and submit DTO | The create-user form likely omits a confirmation control and matching validator. | Add a confirm-password field with cross-field validation before allowing save.
68 | Create New User | Sign-up is not working | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/auth/create-account/ + registration API routes | Registration form may be submitting invalid payload, or backend user-creation flow may be failing. | Trace create-account request and server response; verify validations, payload mapping, and error handling.
29 | Functional Group | Should show confirmation message for deletion | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Delete flow likely removes the record without presenting a dedicated confirmation state/message. | Add a confirmation dialog/banner before delete and verify the correct message renders for the action.
30 | Functional Group | While deleting any fg with existing pwo, its message is not clearly visible. Specially when we scrolled down | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Delete/error message is likely rendering outside the visible viewport or behind the scrolled modal/container. | Anchor the confirmation/error message to the visible modal/footer area or auto-scroll to the alert region.
31 | Functional Group | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Backend audit fields are likely not being populated from the authenticated user context during create/update. | Propagate user identity from auth middleware into create/update handlers and map it into audit columns before persistence.
32 | Primary Work Object | Should allow only 50 character with name | Issue | UI | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Name input is likely missing a max-length validator or the limit is not enforced consistently between UI and backend. | Add matching max-length validation in both form validators and backend DTO/entity rules.
33 | Primary Work Object | Description is not getting saved | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | The create/update payload likely omits these fields or the backend mapper/DTO ignores them on save. | Trace the form control to request payload to persistence mapper and include the missing fields in both create and update flows.
34 | Primary Work Object | Should not allowed duplicate name for same functional group in Add and Edit | Issue | Functional |  | Puneet |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Uniqueness validation is likely missing, scoped incorrectly, or only checked on create but not edit. | Enforce scoped duplicate-name validation in backend and surface the same error path in both add and edit flows.
12 | Industry WRCF Dashboard | On page load, it should display from top. | Issue | UI | not able to replicate case | Yagyesh | 2026-06-04 |  | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ | Dashboard page likely preserves prior scroll state or renders inside a container that is not reset on navigation. | Reset scroll position on page init/navigation completion for the dashboard container.
13 | Industry WRCF Dashboard | In Industry Sector and Industry, two drop down arrow is showing in filters | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ | A custom arrow icon and the native/material arrow are likely both rendering for the same select control. | Remove the duplicate icon source so only one dropdown indicator is shown.
14 | Industry WRCF Dashboard | Header spacing and layout different from other pages | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ | Dashboard layout/styles likely diverged from the shared page-header/card design tokens. | Align CSS spacing, icon treatment, and card/header structure with the approved design pattern.
15 | Industry WRCF Dashboard | Quick action UI is not as per mockup (Icon in Color, Icon and heading in same line, line in between the header and description) | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ | Dashboard layout/styles likely diverged from the shared page-header/card design tokens. | Align CSS spacing, icon treatment, and card/header structure with the approved design pattern.
16 | Industry WRCF Dashboard | Should show Industry Sector and Industry data in sorted order (Alphabetically) | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ | The list is likely rendered in API/default insertion order because no explicit sort is applied before binding the dropdown/list. | Apply deterministic ascending sort in the data adapter or UI mapping before rendering the list.
17 | Industry WRCF Dashboard | While loading page after login, it showing default filters selected but when redirecting from any other page its some time not showing filter data | Issue | Functional | not able to replicate case | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ | Default selection logic is either not running on init or is being overridden by an empty/late data load. | Run selection only after options load, and distinguish default-first-value logic from carry-forward navigation context.
18 | Industry WRCF Dashboard | Logout option is not showing in profile | Issue | Functional | showing sign out button | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/profile/ + layout/profile menu | Profile menu/action list is likely missing the logout entry or hidden by role/config. | Add or re-enable the logout menu action and ensure it is available for authenticated users.
19 | Industry WRCF Dashboard | Quick Action - Edit Structure - Should show default selected industry sector and industry while redirecting from Quick Action | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ + apps/web/admin-portal/src/app/pages/industry-wrcf/ | Dashboard quick-action navigation likely does not preserve selected sector/industry in route state, query params, or shared store. | Pass selected dashboard context into Edit Structure navigation and hydrate the Manage Industry WRCF page from that context before defaulting.
86 | Internship | Mandatory items / fields need to work properly | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/internship/ + internship backend routes | Internship form validation appears incomplete or not consistently enforced across sections. | Audit all mandatory internship fields, align UI markers with validation, and block incomplete saves.
78 | Manage College | Not able to upload College Brochure; upload throws error / is not enabled | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-college/ + file upload API/storage integration | File-upload control may be disabled, misconfigured, or failing during upload request/storage processing. | Check file input enablement, accepted file rules, request payload, and backend upload/storage flow.
79 | Manage Company | Should show edit button for company | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-company/ | Edit action may not be rendered due to missing action binding or permission gating. | Review action controls and permissions so the company edit button is visible and clickable.
80 | Manage Company | Should show company list in alphabetical order | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-company/ | Company list is likely rendered in insertion/API order without an explicit sort. | Apply deterministic ascending sort before binding the company list.
82 | Manage Company | Mandatory fields are not clearly marked / enforced | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-company/ | Required-field indicators and validation rules appear missing or inconsistent in the company form. | Mark required fields clearly and align field validation with business rules.
83 | Manage Company | Should show delete button for company | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-company/ | Delete action may be missing from the action controls or hidden by permission/state logic. | Verify delete action rendering, permissions, and any state conditions suppressing the control.
84 | Manage Company | Difference between Save and Send to Publish should be clear | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-company/ | Workflow states and button intent are not clearly communicated in the UI. | Clarify button labels/help text and ensure draft vs publish behavior is explicit to users.
85 | Manage Company | Light theme UI is inconsistent / not aligned properly | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/manage-company/ + global theme styles | Light-theme styles may be incomplete or not overridden correctly for this page/components. | Compare dark vs light theme styling and fix component-specific CSS/theme token usage.
35 | Primary Work Object | Should show confirmation message for deletion | Issue | Functional | verified | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Delete flow likely removes the record without presenting a dedicated confirmation state/message. | Add a confirmation dialog/banner before delete and verify the correct message renders for the action.
36 | Primary Work Object | While deleting any pwo with existing swo, its message is not clearly visible. Specially when we scrolled down | Issue | Functional | verified | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Delete/error message is likely rendering outside the visible viewport or behind the scrolled modal/container. | Anchor the confirmation/error message to the visible modal/footer area or auto-scroll to the alert region.
37 | Primary Work Object | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional | verified | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Backend audit fields are likely not being populated from the authenticated user context during create/update. | Propagate user identity from auth middleware into create/update handlers and map it into audit columns before persistence.
38 | Secondary Work Object | Should allow only 50 character with name | Issue | UI | verified | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Name input is likely missing a max-length validator or the limit is not enforced consistently between UI and backend. | Add matching max-length validation in both form validators and backend DTO/entity rules.
39 | Secondary Work Object | Description is not getting saved | Issue | Functional | verified | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | The create/update payload likely omits these fields or the backend mapper/DTO ignores them on save. | Trace the form control to request payload to persistence mapper and include the missing fields in both create and update flows.
40 | Secondary Work Object | Should not allowed duplicate name for same Primary work object in Add and Edit | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Uniqueness validation is likely missing, scoped incorrectly, or only checked on create but not edit. | Enforce scoped duplicate-name validation in backend and surface the same error path in both add and edit flows.
41 | Secondary Work Object | Should show confirmation message for deletion (no capability instance available) | Issue | Functional | need clarification by shelendra sir | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Delete flow likely removes the record without presenting a dedicated confirmation state/message. | Add a confirmation dialog/banner before delete and verify the correct message renders for the action.
42 | Secondary Work Object | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional | verified | Yagyesh | 2026-06-04 | Fixed and Raised PR in main | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Backend audit fields are likely not being populated from the authenticated user context during create/update. | Propagate user identity from auth middleware into create/update handlers and map it into audit columns before persistence.
43 | Secondary Work Object | Should show proper error messasge while removing SWO and capability instance mapping available | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/ + WRCF backend routes/repositories | Needs targeted inspection of UI binding, service payload, and backend handling for this flow. | Reproduce on the target environment, inspect request/response payloads, then patch UI binding or backend validation/mapping as needed.
44 | CI Mapping | Mapping popup not to be close while click outside the box | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | Backdrop click is probably not disabled for the mapping dialog. | Disable close-on-backdrop-click for the mapping modal and require explicit close/cancel actions.
45 | CI Mapping | Showing Level twice | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | The display-label builder is inconsistent across modules and is concatenating or omitting label metadata incorrectly. | Centralize label formatting for capability/proficiency and reuse a single formatter across dropdowns and panels.
46 | CI Mapping | Should show Level in bracket like capability | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | The display-label builder is inconsistent across modules and is concatenating or omitting label metadata incorrectly. | Centralize label formatting for capability/proficiency and reuse a single formatter across dropdowns and panels.
47 | CI Mapping | Filters not working properly | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | Filter state is likely not wired correctly to the underlying accordion/query refresh, causing stale or partial data. | Audit filter change handlers and ensure every filter mutation rebuilds the query and refreshes the displayed mapping tree.
48 | CI Mapping | Should show Industry sector, industry and FG in Accordian for all filters | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | Accordion grouping/expand-state logic is likely being built from incomplete mapping data or unstable ordering. | Rebuild the accordion view model from the filtered mapping payload and set explicit default expand/collapse state.
49 | CI Mapping | Should show PWO accordion first expended rest collapse | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | Accordion grouping/expand-state logic is likely being built from incomplete mapping data or unstable ordering. | Rebuild the accordion view model from the filtered mapping payload and set explicit default expand/collapse state.
50 | CI Mapping | Not able to delete capability instance | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | Capability instance delete path is likely blocked by missing delete API handling, stale dependencies, or unhandled child constraints. | Check delete API response, dependency validation, and UI refresh so delete either completes cleanly or shows the correct blocker message.
51 | CI Mapping | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/components/manage-ci-mappings/ + WRCF backend routes | Backend audit fields are likely not being populated from the authenticated user context during create/update. | Propagate user identity from auth middleware into create/update handlers and map it into audit columns before persistence.
52 | Manage WRCF Skills | Should show all the filters default selected as per the values selected in Manage WRCF | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/ | Needs targeted inspection of UI binding, service payload, and backend handling for this flow. | Reproduce on the target environment, inspect request/response payloads, then patch UI binding or backend validation/mapping as needed.
53 | Manage WRCF Skills | Should show Skills, Task & Control Point default first item selected | Issue | Functional |  | Yagyesh |  | in progress | apps/web/admin-portal/src/app/pages/wrcf-skills/ | Child list selection is likely not triggered after data load or after parent filter/context changes. | After loading each child collection, explicitly select the first available item and refresh downstream panels.
54 | Manage WRCF Skills | Should show FG, PWO, SWO as per alphabetic order in filters | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/ | The list is likely rendered in API/default insertion order because no explicit sort is applied before binding the dropdown/list. | Apply deterministic ascending sort in the data adapter or UI mapping before rendering the list. | 2026-04-09 - Still exists
55 | Manage WRCF Skills | In Capability filter, should show code in bracket in last | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/ | The display-label builder is inconsistent across modules and is concatenating or omitting label metadata incorrectly. | Centralize label formatting for capability/proficiency and reuse a single formatter across dropdowns and panels.
56 | Manage WRCF Skills | In proficiency filter, should show level in bracket in last | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/ | The display-label builder is inconsistent across modules and is concatenating or omitting label metadata incorrectly. | Centralize label formatting for capability/proficiency and reuse a single formatter across dropdowns and panels.
57 | Skills | In Add / Edit, Description and Recertification values are not saved | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | The create/update payload likely omits these fields or the backend mapper/DTO ignores them on save. | Trace the form control to request payload to persistence mapper and include the missing fields in both create and update flows.
58 | Skills | Should not allowed duplicate name for same Primary work object in Add and Edit | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Uniqueness validation is likely missing, scoped incorrectly, or only checked on create but not edit. | Enforce scoped duplicate-name validation in backend and surface the same error path in both add and edit flows.
59 | Skills | Should show Cognitive type in ascending order (Add / Edit) | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | The list is likely rendered in API/default insertion order because no explicit sort is applied before binding the dropdown/list. | Apply deterministic ascending sort in the data adapter or UI mapping before rendering the list.
60 | Skills | In delete skill, it should check for task available or not | Issue | Functional |  | Yagyesh |  | in progress | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Delete dependency validation is likely missing or not checking child entities before allowing removal. | Validate downstream dependency counts before delete and block the action with a clear message when children exist.
61 | Task | Remove mandatory option from description | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Description field is likely marked required in the form template even though business rules treat it as optional. | Remove the required marker/validator for Description and align both UI and backend validation rules.
62 | Task | In Add / Edit, Description and Recertification values are not saved | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | The create/update payload likely omits these fields or the backend mapper/DTO ignores them on save. | Trace the form control to request payload to persistence mapper and include the missing fields in both create and update flows.
8 | SignIn page | Should show “Enter a valid password”, instead of “Password must be at least 8 characters.” while password is blank | Issue | UI |  | Yagyesh | 2026-06-04 | Done | apps/web/admin-portal/src/app/pages/login/ + shared auth validators | Blank-password validation is likely falling through to min-length validation instead of required-field validation. | Separate required and min-length validators and show the required-message path when the field is empty.
66 | SignIn page | Forgot password is not working | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/auth/forgot-password/ + auth API routes | Forgot-password submit path may not be wired correctly, or the API call/response handling is failing. | Check forgot-password form submission, API request, validation, and success/error handling end to end.
67 | SignIn page | Google Sign-In is not working | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/auth/ + OAuth/social login integration | Google OAuth redirect/callback configuration or frontend trigger flow may be broken. | Verify Google auth client config, callback URL, popup/redirect flow, and backend token exchange.
63 | Task | Should not allowed duplicate name for same skills in Add and Edit | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Uniqueness validation is likely missing, scoped incorrectly, or only checked on create but not edit. | Enforce scoped duplicate-name validation in backend and surface the same error path in both add and edit flows.
64 | Task | In delete task, it should check for control point available or not | Issue | Functional |  | Yagesh |  | in progress | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Delete dependency validation is likely missing or not checking child entities before allowing removal. | Validate downstream dependency counts before delete and block the action with a clear message when children exist.
65 | Control Point | Unable to create any Control Point | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Control Point save path likely fails due to required-field mismatch, payload mapping issue, or backend create error. | Inspect the create request, validation response, and backend handler to identify whether the failure is UI validation or persistence related.
69 | Skills | Should allow only 50 character with name | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ | Max-length validation is likely missing on the Skill name field in UI and/or backend. | Add consistent max-length validation for Skill name in both frontend form rules and backend validation.
70 | Skills | Should not save when Recertification Cycle (months) is blank in Add / Edit | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Required validation for Recertification Cycle is likely not enforced before save or ignored by backend. | Enforce required validation for Recertification Cycle in UI and backend, and block save with a clear message.
71 | Task | Mandatory fields should be clearly marked with * in Add / Edit | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ | Required-field markers are missing or inconsistently configured in the task form template. | Align UI field labels with actual validation rules and show * only for truly mandatory fields.
72 | Task | Should not allow save without Required Proficiency Level | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Required Proficiency Level validation may be missing or bypassed during create/update. | Make Required Proficiency Level mandatory in form validation and backend request validation.
73 | Task | Should not auto-populate Required Proficiency Level after saving without selection | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | A fallback/default value may be getting assigned server-side or during form rehydration. | Inspect create/update response mapping and default-value logic to stop unintended proficiency assignment.
74 | Control Point | Should not save Control Point when mandatory fields except name are blank | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ + WRCF skills backend routes | Mandatory-field validation for Control Point is likely incomplete in UI and/or backend. | Enforce required validators consistently and reject incomplete Control Point payloads.
75 | Control Point | Should show edit button for Control Point | Issue | UI |  | Yagyesh |  |  | apps/web/admin-portal/src/app/pages/wrcf-skills/components/ | Edit action may not be rendered due to missing permission/UI action binding. | Check action-column rendering and permissions so edit control appears where expected.
76 | Manage Industry WRCF | Should show toaster message for confirmation and error | Issue | UI | pending by saurabh sir's end | Yagyesh |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/ | Success/error toast handling may not be triggered after actions or API responses. | Add centralized success/error toaster calls for create, update, delete, and template actions.
77 | Manage Industry WRCF | Templates are not working | Issue | Functional |  |  |  |  | apps/web/admin-portal/src/app/pages/industry-wrcf/ + template download/upload handlers | Template upload/download action may be pointing to wrong endpoint, disabled handler, or invalid response. | Verify template action wiring, API endpoint, response headers, and error handling.
81 | Navigation | While selecting Manage Company, one more menu item is also selected / highlighted | Issue | UI |  |  |  |  | apps/web/admin-portal/src/app/layout/sidebar/ + route active-state handling | Sidebar active-state logic may be matching multiple routes or using overly broad path checks. | Tighten route matching so only the active menu item is highlighted for the current page.
1 |  | When Clicking on 'Add Skills' from Manage Industry WRCF, values of selected FG, PWO, SWO, Capability, Proficiency do not show up on 'Add Skills' page | Issue |  |  | Yagyesh | 2026-02-04 | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/ + apps/web/admin-portal/src/app/pages/wrcf-skills/ | Selected WRCF context is likely not being passed through navigation state/query params or not being restored on Manage WRCF Skills init. | Check Add Skills navigation payload, route params/shared state, and page-init hydration so FG/PWO/SWO/Capability/Proficiency are carried forward.
2 |  | When Clicking on 'Skill+' from Manage CI Mappings, values of selected FG, PWO, SWO, Capability, Proficiency do not show up on 'Add Skills' page. Rather one cannot enter any value in FG, PWO and CI (SWO, Capability and Proficiency). Without enteriring the FG, PWO and CI values, I am still able to create Skills and Task. What CI's do they get attachd with? | Issue |  | not able to replicate case | puneet |  | Done | apps/web/admin-portal/src/app/pages/industry-wrcf/ + apps/web/admin-portal/src/app/pages/wrcf-skills/ | Selected WRCF context is likely not being passed through navigation state/query params or not being restored on Manage WRCF Skills init. | Check Add Skills navigation payload, route params/shared state, and page-init hydration so FG/PWO/SWO/Capability/Proficiency are carried forward.
3 |  | In Manage Roles, I can't see 'Energy & utilities' sector, while the same is available in the Manage Industry WRCF. Only | Issue |  |  | Yagyesh | 2026-03-04 | Done | apps/web/admin-portal/src/app/pages/wrcf-roles/ | Roles page is likely loading a filtered or stale sector list that is inconsistent with Manage Industry WRCF. | Compare sector fetch/filter logic between Roles and Manage Industry WRCF and unify active-sector source and sorting.
4 |  | From Dashboard, after selecting Thermal Power Plant as Industry, When I click on 'Edit Structure; Industry Sector and Industry shold be auto selected as per Dashboard respective values | Issue |  |  | Yagyesh | 2026-03-04 | Done | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ + apps/web/admin-portal/src/app/pages/industry-wrcf/ | Dashboard quick-action navigation likely does not preserve selected sector/industry in route state, query params, or shared store. | Pass selected dashboard context into Edit Structure navigation and hydrate the Manage Industry WRCF page from that context before defaulting.
5 |  | From Dashboard, after selecting Thermal Power Plant as Industry, When I click on 'Manage Role', it still opens up Industry as 'Steel Manufacturing' | Issue |  |  | Yagyesh | 2026-03-04 | Done | apps/web/admin-portal/src/app/pages/wrcf-dashboard/ + apps/web/admin-portal/src/app/pages/wrcf-roles/ | Manage Role navigation is likely opening with fallback/default industry instead of the currently selected dashboard industry. | Reuse the same carry-forward navigation pattern as Edit Structure and block fallback default selection when explicit dashboard context exists.

## Defect Tracker
S No | Test Case ID | Blocker Type | Priority | Expected Behavior | Actual Behavior | Location | Steps to Reproduce | Envi | Notes / Suggested Fix
1 | WSKILL-E2E-001/002 | Functional Issue | Critical | The selected FG, PWO, SWO, Capability, and Proficiency should be carried forward to the Add Skills page. | After navigating to Add Skills, the selected FG, PWO, SWO, Capability, and Proficiency are missing. | Manage Industry WRCF > Add Skills navigation > Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
2 | WSKILL-E2E-001/002 | Functional Issue | Critical | The selected FG, PWO, SWO, Capability, and Proficiency should be carried forward to the Add Skills page. | After navigating to Add Skills, the selected FG, PWO, SWO, Capability, and Proficiency are missing. | Manage Industry WRCF > Add Skills navigation > Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
3 | ROLE-E2E-001 | Functional Issue | Critical | Manage Roles should show the same active sectors available in Manage Industry WRCF, including Energy & Utilities. | Energy & Utilities is not visible in Manage Roles even though it is available in Manage Industry WRCF. | Dashboard | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
4 | DASH-E2E-026 | Functional Issue | Critical | Edit Structure should open Manage Industry WRCF with the same selected Industry Sector and Industry from Dashboard. | Edit Structure opens Manage Industry WRCF without preserving the selected Dashboard context. | Dashboard > Quick Action > Edit Structure | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
5 | MBUG-005 | Functional Issue | Critical | Manage Role should open with the same selected Industry Sector and Industry from Dashboard. | Manage Role opens with a different industry instead of the selected Dashboard value. | Dashboard > Quick Action > Manage Role | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
6 | NAV-MBUG-006 | Functional Issue | Medium | The obsolete Manage Skill option should not be visible in navigation. | Manage Skill is still visible in the navigation menu. | Sidebar / Navigation menu | 1. Login 2. Observe the sidebar/navigation menu 3. Check the affected item | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
7 | NAV-MBUG-007 | UI/UX Issue | Medium | Manage Company should display its navigation icon. | Manage Company appears without the expected icon. | Sidebar / Navigation menu | 1. Login 2. Observe the sidebar/navigation menu 3. Check the affected item | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
8 | LOGIN-MBUG-008 | UI/UX Issue | Low | When the password field is blank, the login form should show “Enter a valid password”. | When the password field is blank, the form shows “Password must be at least 8 characters.” | Login page > Password validation | 1. Open Login page 2. Leave password blank 3. Trigger validation 4. Observe the message | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
9 | USER-MBUG-009 | UI/UX Issue | Low | The password show/hide control should align properly with the password input. | The password show/hide control is misaligned with the input field. | Create New User form | 1. Open Create New User 2. Inspect the affected field or control 3. Observe the behavior | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
10 | USER-MBUG-010 | UI/UX Issue | Low | The form should use one consistent label for the email field. | The UI uses both “E-mail” and “Email Address”, which is inconsistent. | Create New User form | 1. Open Create New User 2. Inspect the affected field or control 3. Observe the behavior | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
11 | USER-MBUG-011 | UI/UX Issue | Low | Create New User should include a confirm password field. | Create New User does not provide a confirm password option. | Create New User form | 1. Open Create New User 2. Inspect the affected field or control 3. Observe the behavior | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
12 | DASH-MBUG-001 | UI/UX Issue | Low | Dashboard should open from the top of the page on load. | Dashboard does not start at the top when the page loads. | Dashboard | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
13 | DASH-MBUG-002 | UI/UX Issue | Low | Each filter should show only one dropdown arrow. | Industry Sector and Industry filters show two dropdown arrows. | Dashboard > Industry Sector / Industry filters | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
14 | DASH-MBUG-003 | UI/UX Issue | Low | Dashboard header spacing and layout should match the standard page pattern. | Dashboard header spacing/layout is inconsistent with other pages. | Dashboard | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
15 | DASH-MBUG-005 | UI/UX Issue | Low | Quick Action tiles should match the approved mockup styling. | Quick Action tiles differ from the mockup in icon color, alignment, and separators. | Dashboard | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
16 | DASH-E2E-004/006 | Functional Issue | Medium | The relevant dropdown/list values should be shown in ascending alphabetical order. | The relevant dropdown/list values are not shown in ascending alphabetical order. | Dashboard > Industry Sector / Industry filters | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
17 | DASH-E2E-002/003 | Functional Issue | Medium | The correct default or carried-forward Industry Sector and Industry should be selected automatically. | The expected Industry Sector and Industry are not selected automatically. | Dashboard | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
18 | DASH-MBUG-006 | Functional Issue | Medium | The profile menu should include a logout option. | The profile menu does not show a logout option. | Dashboard > Profile menu | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
19 | DASH-E2E-026 | Functional Issue | Critical | Edit Structure should open Manage Industry WRCF with the same selected Industry Sector and Industry from Dashboard. | Edit Structure opens Manage Industry WRCF without preserving the selected Dashboard context. | Dashboard > Quick Action > Edit Structure | 1. Login 2. Open Dashboard 3. Perform the affected action 4. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
20 | MIWRCF-MBUG-020 | UI/UX Issue | Low | Proficiency labels should follow the same readable label format as capability values, including the level text. | Proficiency values do not follow the expected label format. | Manage Industry WRCF | 1. Login 2. Open Manage Industry WRCF 3. Select sector/industry as needed 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
21 | MIWRCF-MBUG-021 | UI/UX Issue | Low | Upload and Download Template actions should show the correct icons. | Upload/Download Template actions are using the wrong icons. | Manage Industry WRCF > Template actions | 1. Login 2. Open Manage Industry WRCF 3. Select sector/industry as needed 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
22 | DASH-E2E-026 | Functional Issue | Critical | Edit Structure should open Manage Industry WRCF with the same selected Industry Sector and Industry from Dashboard. | Edit Structure opens Manage Industry WRCF without preserving the selected Dashboard context. | Dashboard > Quick Action > Edit Structure | 1. Login 2. Open Manage Industry WRCF 3. Select sector/industry as needed 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
23 | MIWRCF-E2E-002/004 | Functional Issue | Medium | The relevant dropdown/list values should be shown in ascending alphabetical order. | The relevant dropdown/list values are not shown in ascending alphabetical order. | Manage Industry WRCF | 1. Login 2. Open Manage Industry WRCF 3. Select sector/industry as needed 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
24 | MIWRCF-E2E-010/012/015/017/020 | Functional Issue | Medium | Should show default first value selected for FG, PWO and SWO, capability and Proficiency (in green if any mapped). | The current behavior does not match the expected outcome described for this issue. | Manage Industry WRCF | 1. Login 2. Open Manage Industry WRCF 3. Select sector/industry as needed 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
25 | MIWRCF-E2E-009/011/014 | Functional Issue | Medium | The relevant dropdown/list values should be shown in ascending alphabetical order. | The relevant dropdown/list values are not shown in ascending alphabetical order. | Manage Industry WRCF | 1. Login 2. Open Manage Industry WRCF 3. Select sector/industry as needed 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
26 | FG-E2E-006 | UI/UX Issue | Low | The name field should limit input to 50 characters. | The name field allows values beyond 50 characters or does not enforce the limit properly. | Manage Industry WRCF > Functional Group | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
27 | FG-E2E-014 | Functional Issue | Medium | The relevant dropdown/list values should be shown in ascending alphabetical order. | The relevant dropdown/list values are not shown in ascending alphabetical order. | Manage Industry WRCF > Functional Group | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
28 | FG-E2E-009/010 | Functional Issue | Medium | Duplicate names within the same parent scope should be blocked in Add and Edit. | Duplicate names are allowed or not blocked consistently in Add/Edit. | Manage Industry WRCF > Functional Group | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
29 | FG-E2E-022 | Functional Issue | Medium | Delete should show a confirmation message before the item is removed. | Delete does not show the expected confirmation message. | Manage Industry WRCF > Functional Group | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
30 | FG-MBUG-030 | UI/UX Issue | Medium | The delete/error message should remain clearly visible to the user. | The delete/error message is partially hidden or unclear, especially after scrolling. | Manage Industry WRCF > Functional Group | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
31 | FG-MBUG-031 | Data Issue | Medium | CreatedBy and UpdatedBy should store the correct user id in the database. | CreatedBy and UpdatedBy are not capturing the correct user id. | Manage Industry WRCF > Functional Group | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
32 | PWO-E2E-005 | UI/UX Issue | Low | The name field should limit input to 50 characters. | The name field allows values beyond 50 characters or does not enforce the limit properly. | Manage Industry WRCF > Primary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
33 | PWO-MBUG-033 | Functional Issue | Medium | Description should be saved and visible after create/edit. | Description is not saved after create/edit. | Manage Industry WRCF > Primary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
34 | PWO-E2E-006/007/012 | Functional Issue | Medium | Duplicate names within the same parent scope should be blocked in Add and Edit. | Duplicate names are allowed or not blocked consistently in Add/Edit. | Manage Industry WRCF > Primary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
35 | PWO-E2E-015 | Functional Issue | Medium | Delete should show a confirmation message before the item is removed. | Delete does not show the expected confirmation message. | Manage Industry WRCF > Primary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
36 | PWO-MBUG-036 | UI/UX Issue | Medium | The delete/error message should remain clearly visible to the user. | The delete/error message is partially hidden or unclear, especially after scrolling. | Manage Industry WRCF > Primary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
37 | PWO-MBUG-037 | Data Issue | Medium | CreatedBy and UpdatedBy should store the correct user id in the database. | CreatedBy and UpdatedBy are not capturing the correct user id. | Manage Industry WRCF > Primary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
38 | SWO-E2E-005 | UI/UX Issue | Low | The name field should limit input to 50 characters. | The name field allows values beyond 50 characters or does not enforce the limit properly. | Manage Industry WRCF > Secondary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
39 | SWO-MBUG-039 | Functional Issue | Medium | Description should be saved and visible after create/edit. | Description is not saved after create/edit. | Manage Industry WRCF > Secondary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
40 | SWO-E2E-006/007/012 | Functional Issue | Medium | Duplicate names within the same parent scope should be blocked in Add and Edit. | Duplicate names are allowed or not blocked consistently in Add/Edit. | Manage Industry WRCF > Secondary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
41 | SWO-E2E-015 | Functional Issue | Medium | Delete should show a confirmation message before the item is removed. | Delete does not show the expected confirmation message. | Manage Industry WRCF > Secondary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
42 | SWO-MBUG-042 | Data Issue | Medium | CreatedBy and UpdatedBy should store the correct user id in the database. | CreatedBy and UpdatedBy are not capturing the correct user id. | Manage Industry WRCF > Secondary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
43 | SWO-E2E-017 | Functional Issue | Medium | Should show proper error messasge while removing SWO and capability instance mapping available. | The current behavior does not match the expected outcome described for this issue. | Manage Industry WRCF > Secondary Work Object | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
44 | CIMAP-E2E-026 | UI/UX Issue | Low | The mapping popup should stay open when the user clicks outside the dialog. | The mapping popup closes when the user clicks outside it. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
45 | CIMAP-MBUG-001 | Functional Issue | Medium | Level should be shown only once in the label. | Level is shown twice in the UI. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
46 | CIMAP-E2E-016 | Functional Issue | Medium | Level should be shown once in brackets, similar to capability formatting. | Level formatting does not match the expected bracketed format. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
47 | CIMAP-E2E-031/032/033 | Functional Issue | Critical | All filters should correctly refine the displayed CI Mapping data. | CI Mapping filters do not consistently update or filter the displayed data. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
48 | CIMAP-E2E-012/013/014 | Functional Issue | Medium | All filters should show Industry Sector, Industry, and FG values in the accordion structure. | The accordion does not consistently show Industry Sector, Industry, and FG across filters. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
49 | CIMAP-E2E-015 | Functional Issue | Medium | The PWO accordion should be expanded by default while others remain collapsed. | The accordion default expand/collapse state is incorrect. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
50 | CIMAP-E2E-021/022/023/024 | Functional Issue | Critical | Capability Instance should be deletable when allowed, or show a clear blocking reason. | Capability Instance cannot be deleted as expected. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
51 | CIMAP-MBUG-051 | Data Issue | Medium | CreatedBy and UpdatedBy should store the correct user id in the database. | CreatedBy and UpdatedBy are not capturing the correct user id. | Manage Industry WRCF > CI Mapping | 1. Login 2. Open Manage Industry WRCF 3. Select the required context 4. Open the affected section 5. Perform the action 6. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
52 | WSKILL-E2E-001/002 | Functional Issue | Medium | Manage WRCF Skills filters should auto-select based on the chosen Manage WRCF values. | Manage WRCF Skills filters do not reflect the selected Manage WRCF context. | Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
53 | WSKILL-E2E-006/007/008 | Functional Issue | Medium | Skills, Task, and Control Point should auto-select the first available item. | Skills, Task, and Control Point do not auto-select the first available item. | Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
54 | WSKILL-E2E-004 | Functional Issue | Medium | The relevant dropdown/list values should be shown in ascending alphabetical order. | The relevant dropdown/list values are not shown in ascending alphabetical order. | Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
55 | WSKILL-MBUG-001 | Functional Issue | Medium | Capability values should display the code in brackets. | Capability values do not show the code in brackets as expected. | Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
56 | WSKILL-MBUG-002 | Functional Issue | Medium | Level should be shown once in brackets, similar to capability formatting. | Level formatting does not match the expected bracketed format. | Manage WRCF Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
57 | SKL-MBUG-001 | Functional Issue | Medium | Description and Recertification values should be saved after create/edit. | Description and Recertification values are not saved after create/edit. | Manage WRCF Skills > Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
58 | SKL-E2E-006/007/015 | Functional Issue | Medium | Duplicate names within the same parent scope should be blocked in Add and Edit. | Duplicate names are allowed or not blocked consistently in Add/Edit. | Manage WRCF Skills > Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
59 | SKL-MBUG-003 | Functional Issue | Medium | The relevant dropdown/list values should be shown in ascending alphabetical order. | The relevant dropdown/list values are not shown in ascending alphabetical order. | Manage WRCF Skills > Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
60 | SKL-E2E-013 | Functional Issue | Medium | Delete Skill should check for dependent Tasks before allowing deletion. | Skill deletion does not correctly block when dependent Tasks exist. | Manage WRCF Skills > Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
61 | TSK-MBUG-001 | UI/UX Issue | Low | Description should not be marked as mandatory. | Description is incorrectly marked as mandatory. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
62 | TSK-MBUG-002 | Functional Issue | Medium | Description and Recertification values should be saved after create/edit. | Description and Recertification values are not saved after create/edit. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
63 | TSK-E2E-005/006 | Functional Issue | Medium | Duplicate names within the same parent scope should be blocked in Add and Edit. | Duplicate names are allowed or not blocked consistently in Add/Edit. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
64 | TSK-E2E-011 | Functional Issue | Medium | Delete Task should check for dependent Control Points before allowing deletion. | Task deletion does not correctly block when dependent Control Points exist. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
65 | CP-E2E-005 | Functional Issue | Critical | Users should be able to create a Control Point when valid required data is provided. | Control Point creation does not complete successfully. | Manage WRCF Skills > Control Point | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Perform the affected action 5. Observe the result | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
66 | LOGIN-MBUG-001 | Functional Issue | Medium | Forgot Password should work end to end for a valid registered email. | Forgot Password flow does not complete successfully. | SignIn > Forgot Password | 1. Open login page 2. Click Forgot Password 3. Submit valid email 4. Observe response | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
67 | LOGIN-MBUG-002 | Functional Issue | Medium | Google Sign-In should authenticate successfully and return the user to the app. | Google Sign-In does not complete successfully. | SignIn > Google Sign-In | 1. Open login page 2. Click Google Sign-In 3. Complete auth flow | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
68 | SKL-MBUG-004 | Functional Issue | Medium | Skill name should be limited to 50 characters. | Skill name accepts more than 50 characters or is not blocked consistently. | Manage WRCF Skills > Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Open Add/Edit Skill 5. Enter more than 50 characters in Name 6. Save | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
69 | SKL-MBUG-005 | Functional Issue | Medium | Skill should not save when Recertification Cycle (months) is blank. | Skill save is allowed when Recertification Cycle (months) is blank. | Manage WRCF Skills > Skills | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Open Add/Edit Skill 5. Leave Recertification Cycle blank 6. Save | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
70 | TSK-MBUG-004 | UI/UX Issue | Low | All mandatory Task fields should be clearly marked with *. | Mandatory Task fields are not clearly marked with * consistently. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Open Add/Edit Task 5. Observe field labels | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
71 | TSK-MBUG-005 | Functional Issue | Medium | Task should not save without Required Proficiency Level. | Task save is allowed without selecting Required Proficiency Level. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Open Add/Edit Task 5. Leave Required Proficiency Level blank 6. Save | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
72 | TSK-MBUG-006 | Functional Issue | Medium | Task should not auto-populate Required Proficiency Level after save when no selection was made. | Task gets an unintended Required Proficiency Level after save. | Manage WRCF Skills > Task | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Open Add/Edit Task 5. Save without selecting Required Proficiency Level 6. Reopen record | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
73 | CP-E2E-004 | Functional Issue | Critical | Control Point should not save when mandatory fields are blank. | Control Point save is allowed or not blocked correctly when mandatory fields are blank. | Manage WRCF Skills > Control Point | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Open Create Control Point 5. Leave mandatory fields blank 6. Save | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
74 | CP-MBUG-002 | UI/UX Issue | Low | Edit button should be visible for existing Control Point records. | Edit button is not visible for Control Point where users expect it. | Manage WRCF Skills > Control Point | 1. Login 2. Open Manage WRCF Skills 3. Select the required filters/context 4. Observe existing Control Point actions | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
75 | MIWRCF-MBUG-003 | UI/UX Issue | Low | Manage Industry WRCF should show confirmation and error toaster messages for actions. | Expected confirmation/error toaster messages are not shown consistently. | Manage Industry WRCF | 1. Login 2. Open Manage Industry WRCF 3. Trigger successful and error actions 4. Observe toasters | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
76 | MIWRCF-MBUG-004 | Functional Issue | Medium | Template upload/download actions should work correctly in Manage Industry WRCF. | Template actions are not working correctly. | Manage Industry WRCF > Template actions | 1. Login 2. Open Manage Industry WRCF 3. Click download template 4. Try upload template if available | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.
77 | NAV-MBUG-001 | UI/UX Issue | Low | Only the active sidebar menu item should be highlighted. | Selecting Manage Company also highlights an unrelated menu item. | Navigation > Sidebar | 1. Login 2. Open Manage Company 3. Observe sidebar highlight state | test | Business-facing defect entry derived from Technical Analysis; verify manually on the target environment before closure.

## Sheet1
Whizard Issue Tracker
S.No. | Module | Item Description | New Requirement / Change Request / Issue | Type | Next Action | Responsibility | Resolution Date | Status
1 |  | When Clicking on 'Add Skills' from Manage Industry WRCF, values of selected FG, PWO, SWO, Capability, Proficiency do not show up on 'Add Skills' page | Issue |  |  | Yagyesh | 2026-02-04 | Fixed and Raised PR in main
2 |  | When Clicking on 'Skill+' from Manage CI Mappings, values of selected FG, PWO, SWO, Capability, Proficiency do not show up on 'Add Skills' page. Rather one cannot enter any value in FG, PWO and CI (SWO, Capability and Proficiency). Without enteriring the FG, PWO and CI values, I am still able to create Skills and Task. What CI's do they get attachd with? | Issue |  | not able to replicate case | Yagyesh
3 |  | In Manage Roles, I can't see 'Energy & utilities' sector, while the same is available in the Manage Industry WRCF. Only | Issue |  |  | Yagyesh | 2026-03-04 | Fixed and Raised PR in main
4 |  | From Dashboard, after selecting Thermal Power Plant as Industry, When I click on 'Edit Structure; Industry Sector and Industry shold be auto selected as per Dashboard respective values | Issue |  |  | Yagyesh | 2026-03-04 | Fixed and Raised PR in main
5 |  | From Dashboard, after selecting Thermal Power Plant as Industry, When I click on 'Manage Role', it still opens up Industry as 'Steel Manufacturing' | Issue |  |  | Yagyesh | 2026-03-04 | Fixed and Raised PR in main
6 | Navigation | Logout option is not showing in profile | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
7 | Navigation | Icon not showing for manage company | Issue | Functional | showing in my case | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
8 | SignIn page | Should show “Enter a valid password”, instead of “Password must be at least 8 characters.” while password is blank | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
9 | Create New User | In Password, Show/Hide to be align with box | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
10 | Create New User | E-mail and Email Address, what is the difference | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
11 | Create New User | Should option for confirm password | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
12 | Industry WRCF Dashboard | On page load, it should display from top. | Issue | UI | not able to replicate case | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
13 | Industry WRCF Dashboard | In Industry Sector and Industry, two drop down arrow is showing in filters | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
14 | Industry WRCF Dashboard | Header spacing and layout different from other pages | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
15 | Industry WRCF Dashboard | Quick action UI is not as per mockup (Icon in Color, Icon and heading in same line, line in between the header and description) | Issue | UI
16 | Industry WRCF Dashboard | Should show Industry Sector and Industry data in sorted order (Alphabetically) | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
17 | Industry WRCF Dashboard | While loading page after login, it showing default filters selected but when redirecting from any other page its some time not showing filter data | Issue | Functional | not able to replicate case | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
18 | Industry WRCF Dashboard | Logout option is not showing in profile | Issue | Functional | showing sign out button | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
19 | Industry WRCF Dashboard | Quick Action - Edit Structure - Should show default selected industry sector and industry while redirecting from Quick Action | Issue | Functional
20 | Manage Industry WRCF | Should show proficiency level like capability … Label (Level) | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
21 | Manage Industry WRCF | Change icon for Upload and download template | Issue | UI
22 | Manage Industry WRCF | Should show default industry sector and industry selected 1. From Navigation, should show default first value selected 2. From Edit Structure, should show default dashboard selected values | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
23 | Manage Industry WRCF | Should show Industry sector and industry in alphabetic sorted order (ascending) | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
24 | Manage Industry WRCF | Should show default first value selected for FG, PWO and SWO, capability and Proficiency (in green if any mapped) | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
25 | Manage Industry WRCF | Should show FG, PWO and SWO in alphabetic order | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
26 | Functional Group | Should allow only 50 character with name | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
27 | Functional Group | Should show Domain type in ascending alphabetic order | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
28 | Functional Group | Should not allowed duplicate name for same industry in Add and Edit | Issue | Functional
29 | Functional Group | Should show confirmation message for deletion | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
30 | Functional Group | While deleting any fg with existing pwo, its message is not clearly visible. Specially when we scrolled down | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
31 | Functional Group | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
32 | Primary Work Object | Should allow only 50 character with name | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
33 | Primary Work Object | Description is not getting saved | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
34 | Primary Work Object | Should not allowed duplicate name for same functional group in Add and Edit | Issue | Functional
35 | Primary Work Object | Should show confirmation message for deletion | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
36 | Primary Work Object | While deleting any pwo with existing swo, its message is not clearly visible. Specially when we scrolled down | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
37 | Primary Work Object | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
38 | Secondary Work Object | Should allow only 50 character with name | Issue | UI |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
39 | Secondary Work Object | Description is not getting saved | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
40 | Secondary Work Object | Should not allowed duplicate name for same Primary work object in Add and Edit | Issue | Functional
41 | Secondary Work Object | Should show confirmation message for deletion (no capability instance available) | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
42 | Secondary Work Object | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional |  | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
43 | Secondary Work Object | Should show proper error messasge while removing SWO and capability instance mapping available | Issue | Functional
44 | CI Mapping | Mapping popup not to be close while click outside the box | Issue | UI
45 | CI Mapping | Showing Level twice | Issue | Functional
46 | CI Mapping | Should show Level in bracket like capability | Issue | Functional
47 | CI Mapping | Filters not working properly | Issue | Functional
48 | CI Mapping | Should show Industry sector, industry and FG in Accordian for all filters | Issue | Functional
49 | CI Mapping | Should show PWO accordion first expended rest collapse | Issue | Functional
50 | CI Mapping | Not able to delete capability instance | Issue | Functional
51 | CI Mapping | In DB, CreatedBy and UpdatedBy not capturing the user id | Issue | Functional
52 | Manage WRCF Skills | Should show all the filters default selected as per the values selected in Manage WRCF | Issue | Functional | already done previously in on S. No 2 | Yagyesh | 2026-06-04 | Fixed and Raised PR in main
53 | Manage WRCF Skills | Should show Skills, Task & Control Point default first item selected | Issue | Functional
54 | Manage WRCF Skills | Should show FG, PWO, SWO as per alphabetic order in filters | Issue | Functional
55 | Manage WRCF Skills | In Capability filter, should show code in bracket in last | Issue | Functional
56 | Manage WRCF Skills | In proficiency filter, should show level in bracket in last | Issue | Functional
57 | Skills | In Add / Edit, Description and Recertification values are not saved | Issue | Functional
58 | Skills | Should not allowed duplicate name for same Primary work object in Add and Edit | Issue | Functional
59 | Skills | Should show Cognitive type in ascending order (Add / Edit) | Issue | Functional
60 | Skills | In delete skill, it should check for task available or not | Issue | Functional
61 | Task | Remove mandatory option from description | Issue | UI
62 | Task | In Add / Edit, Description and Recertification values are not saved | Issue | Functional
63 | Task | Should not allowed duplicate name for same skills in Add and Edit | Issue | Functional
64 | Task | In delete task, it should check for control point available or not | Issue | Functional
65 | Control Point | Unable to create any Control Point | Issue | Functional